## Sheet1
Task | Charlotte | Costas | Dalia | Dima | Han | Consolidated (all estimates in hours)
Create a log in page |  | 2 | 2 | 1 |  | 2
Use our internal database to identify and authenticate users logging in |  | 4 | 6 | 5 |  | 5
Access the account information from our internal DB which stores the user inputs such as their calendar and transportation preferences to do refresh |  | 3 | 1 | 2 |  | 3
Refresh every time the user opens app/returns to home page |  | 2 | 2 | 2 |  | 4
Create UI/interface |  | 9 | 10 | 7 |  | 8
Get Next Scheduled Location from our stored database(google calendar user data) |  | 1 | 1 | 1 |  | 2
Display current location and next scheduled location on the map on UI |  | 5 | 1 | 3 |  | 2
Display live weather icon and set up API call |  | 2 | 1 | 1 |  | 3
Display/build interactive options menu |  | 5 | 3 | 3 |  | 5
Get time estimations to next location API calls to: (Uber, Lyft, MBTA, and google maps walking estimation) |  | 12 | 10 | 8 |  | 10
Build a scrolling menu that displays the above information |  | 2 | 3 | 2 |  | 5
Total | 0 | 47 | 40 | 35 | 0 | 49