## Sheet1
Task | Charlotte | Costas | Dalia | Dima | Han | Consolidated (all estimates in hours)
Create a log in page | 2 | 2 | 2 | 1 | 3 | 2
Use our internal database to identify and authenticate users logging in | 5 | 4 | 6 | 5 | 6 | 5
Access the account information from our internal DB which stores the user inputs such as their calendar and transportation preferences to do refresh | 3 | 3 | 1 | 2 | 4 | 3
Refresh every time the user opens app/returns to home page | 1 | 2 | 2 | 2 | 4 | 4
Create UI/interface | 8 | 9 | 10 | 7 | 12 | 8
Get Next Scheduled Location from our stored database(google calendar user data) | 1 | 1 | 1 | 1 | 2 | 2
Display current location and next scheduled location on the map on UI | 3 | 5 | 1 | 3 | 4 | 2
Display live weather icon and set up API call | 1 | 2 | 1 | 1 | 4 | 3
Display/build interactive options menu | 5 | 5 | 3 | 3 | 6 | 5
Get time estimations to next location API calls to: (Uber, Lyft, MBTA, and google maps walking estimation) | 10 | 12 | 10 | 8 | 12 | 10
Build a scrolling menu that displays the above information | 3 | 2 | 3 | 2 | 4 | 5
Total | 42 | 47 | 40 | 35 | 61 | 49